## Control
Audit No. | Findings | CAR No. | Audit Title /Follow up | Div/Sta. Affec.1 | Div/Sta. Affec.2 | AMU BASE/OUT STATION | Area Concerned | Location | Reg. No. | Level | Letter Number | Issue date | Reply Due date | Leter No. | LetterDate | Result1 | Leter No. | LetterDate | Result2 | Leter No. | LetterDate | Result3 | Letter No. | LetterDate | Result4 | Leter No. | LetterDate | Result5 | Leter No. | LetterDate | Result6 | Leter No. | LetterDate | Result7 | Leter No. | LetterDate | Result8 | Leter No. | LetterDate | Result9 | Leter No. | LetterDate | Result10 | Leter No. | LetterDate | Result11 | Final-Letter Number | Final-Issue date | Final-Reply Due date | Final-Days Left | Result (before close) | Status | Ref. | Finding | Corrective Action | CA Target Date | Preventive Action | PA Target Date | Verify Date | Internal Reject | Response Overdue (Internal) | Response Overdue (External) | Extension Applied | AACM/3rd Party Reject | CA/PA Extension Applied
1 | 1 | AOC/01/13-25 | AOC Audit | ED |  | AMU BASE | Cabin Safety | MFM | B-MAN | 2 | 2671/DFSL/13 | 2013-12-12 | 2013-12-31 | OCS to CQD May Zhang | 2014-01-09 | Answered | 0099/DFSL/14 | 2014-01-14 | Rejected | CQD/016/14 | 2014-01-29 | Extension | 0314/DFSL/14 | 2014-02-12 | Extension Approved | OCS to CQD May | 2014-02-14 | Answered | CQD/020/14 | 2014-02-17 | Answered | [15 empty] | CQD-020/14 | 2014-02-17 | N/A | N/A |  | Open | ANRM Part III para 12(4). | During the ramp inspection on aircraft B-MAN. it was found that a great number of the sample checked life-vests were difficult andlor not easy to take out from the pocket assembly beneath passenger seats by a male inspector in a normal seated position. The operating crew on that particularly night as well as the maintenance personnel on duty were being notified by AACM inspector at the time of the inspection. | On 21 Jan 2014, ED issued work order AM15584473 (as attachment 1) to inspect the life-vests on B-MAN. All the difficult opening belt buckle (total 59) of the life-vests pockets were opened and closed several times, after that, they could be easily opened. All life-vests were taken out from the pocket assembly beneath all passenger seats, and were installed back without difficulty. | N/A | 1) Work orders have been issued by ED to inspect the life-vests on rest of AMU aircrafts (as attachment 2) before 31 Jan 2014. The belt buckles which are reported "too tight" will be summarized by system engineer and be replaced before July 2014, when spares are available. 2) ED decides to inspect the life-vest pockets in every C-Check through CMP task 250000-AM-3 (as attachment 3, CMP TR No. A320/CMPR8.01/TR18) to avoid similar case happening again. | 2014-07-31 |  | 1 |  |  |  | 1
2 | 1 | A/196/13-2/6 | TPE Station Audit | MRD |  | AMU BASE | Equipment, Tool & Material | TPE | N/A | 2 | 2759/DFSL/13 | 2013-12-30 | 2014-01-15 | OCS to CQD May Zhang | 2014-01-14 | Answered | 0240/DFSL/14 | 2014-01-28 | Accepted & Closed | [27 empty] | 0240/DFSL/14 | 2014-01-28 | N/A | N/A |  | Closed | MEPM 2.3.2 - Shelf Life Control, MEPM 2.3.3 Issue of Aircraft Parts and Materials | MEPM 2.3.2 states the procedure for the control of shelf life items and MEPM 2.3.3 states the procedure for the issue of aircraft parts and materials within Air Macau. During the audit, TPE store was sample checked. Replacement Cartridge, p/n: 778000 RSA2, gea were found all with Material Sticker bearing some with shelf life as "30APR2022" and some with shelf life as "NA". Further checking on AMASIS with TPE storekeeper during the time of audit could not identify any stated shelf life for item with this p/n: 778000 RSA2 within the AMASIS database. | 1) MRD decided to classify the type of material as " shelf life control" items in system due to AMASIS can't control 2 different types ( type 1: No expiry date; type 2 : shelf life control) in one PN at the same time. 2) Called back all filters with PN 778000 from TPE store for reidentification according to certificates, Please see attached email. 3) Revised the expiry date of PN 778000 which shows" No Expiry Date" on the certificate to " 10 years term" in AMASIS record according to MR internal agreement. Please find attached system records for your reference. | N/A | Internal memo was issued to MR Receiving Group and requested all of them to perform related procedure, Please see attached memo. | 2014-03-31
| 2 | A/196/13-3/6 | TPE Station Audit | QD |  | AMU BASE | Maintenance Procedures and Quality System | TPE | N/A | 2 | 2759/DFSL/13 | 2013-12-30 | 2014-01-15 | OCS to CQD May Zhang | 2014-01-13 | Answered | 0240/DFSL/14 | 2014-01-28 | Accepted & Evidence | [27 empty] | 0240/DFSL/14 | 2014-01-28 | Next MEPM R20 | N/A | Need to send the published MEPM R20 Chapter 1.7.2 to AACM for final closure | Open | MAR-145.65(b) - Maintenance Procedures and Quality System | MAR 145.65(b) states in part that the approved maintenance organisation must establ ish procedures acceptable to the AACM taking into account human factors and human performance to ensure good maintenance practices and compliance with all relevant requirements in MAR-145. During the audit. on duty certifying staff. Mr. HUNG Fu Cheng provided his authorization document that bears the stamp sample, no. 30, which matched his in-use authorization stamp, no. 30. However, Mr. YU Yukuang , provided his authorization document that bears no stamp sample but a "01 No. 31" in the authorization content, which did not match his in-use authorization stamp, no. 31A. In addition, there was no authorization holder signature on the authorization document (PM 1.7.1-01-0), which reflect the acceptance and full conversant with the terms, duties and responsibilities, as stated on the authorization document and in MEPM. | 1. "DI No. 31" in the authorization indicates Mr. YU Yukuang is a Delegated Inspector (DI) with authorization No. 31. Triangle shape of his in-use authorization stamp stands for the DI authorization. "A" in "31A" stands for Stamp Issue No. The MEPM R19 Chapter 1.7.2 paragraph 11.1 states when replacing stamp, "a new stamp with the same authorisation number but new issue number shall be issued". (Attachment 1 of 4) 2. The stamp control process has been enhanced in which the staff signature & stamp are no longer required on the authorization letter. However, relevant MEPM procedure will be published on the next MEPM revision. (Attachment 2 of 4) 3. With regards to deviating MEPM R19 Chapter 1.7.2 paragraph 11.2, a Concession CON-2014-001 was raised to approve the deviation. (Attachment 3 of 4). | N/A | Instruction has been made to all quality assurance engineers stating "Process improvement shall be made after procedure amendment. Process improvement requires immediate implementation which reflecting current MEPM shall be made through concession application." (Attachment 4 of 4) | 2014-01-09
| 3 | A/196/13-4/6 | TPE Station Audit | ED |  | AMU BASE | Maintenance Data | TPE | N/A | 2 | 2759/DFSL/13 | 2013-12-30 | 2014-01-15 | OCS to CQD May Zhang | 2014-01-16 | Answered | 0240/DFSL/14 | 2014-01-28 | Rejected | CQD/017/14 | 2014-02-11 | Answered | [24 empty] | CQD/017/14 | 2014-02-11 | N/A | N/A |  | Open | MAR-145.45(a) - Maintenance Data | MAR 145.45(a) states in part that "the approved maintenance organisation must hold and use applicable current maintenance data .. . ". During the audit, it was observed from the "Air Macau A320 Fleet Techinical Notice (TN) List" dated 12/13/2013 that a number of TN's (e.g. 00228, 00231 , 00281 , 00299) are applicable to aircrafts B-MAB and B-MAR, which had already been de-registered in July and May 2013 respectively. | Review all TN. Cancel related TNs which are only applicable for MAR and MAB, including TN 00228, 00231, 00281, 00299. If the TNs are applicable for whole fleet, they will be revised at next revision. The final revised control list is attached. | Next TN Revision | Because it is not affect aircraft effectivity and airworthiness, it will be based on annual review to remove not applicable TN due to Aircraft phase-out. The request is added in ED reminder list. | 2014-02-11 | [5 empty] | 1
| 4 | A/196/13-5/6 | TPE Station Audit | ED | AMD | AMU BASE | Maintenance Data | TPE | N/A | 2 | 2759/DFSL/13 | 2013-12-30 | 2014-01-15 | OCS to CQD May Zhang | 2014-01-16 | Answered | 0240/DFSL/14 | 2014-01-28 | Accepted & Closed | [27 empty] | 0240/DFSL/14 | 2014-01-28 | N/A | N/A |  | Closed | MAR-145.45(a) - Maintenance Data | MAR 145.45(a) states that the MAR-145 approved maintenance organisation must hold and use applicable current maintenance data in the performance of maintenance including modifications and repairs. Applicable means relevant to any aircraft, aircraft component or process specified in the MAR-145 approved maintenance organisation's approval class rating schedule and any associated capability list. During the audit, LM staff was sample checked to look for supplementary maintenance information for post cabin reconfigured (modification) aircrafts i.e. B-MAL, B-MAN and B-MAM. Despite a TN A320-00310 had been issued, the maintenance personnel could not locate the maintenance data requested by the auditor in the first place. Eventually, a CD was provided by the TPE station Aircraft Maintenance Manager, in which not all the supplementary maintenance information as stated in TN A320-00310 were included. Note: This is a re-occurringfinding. | 1. To improve the working performance, AMD requested ED on 19 Jul 2013 to send the cabin supplement manuals in CD to TPE station through technical library. (as attachment 1) 2. ED system engineer selected LM related cabin supplement manuals, asked technical library to send them to TPE station in CD. 3. TPE LM did receive a CD named "Air Macau Cabin Supplement Manual" on 24 Jul 2013 from technical library as controlled manual (as attachment 2). 4. This CD was wrongly removed from "The Manual List in Outstation [Taipei]" dated 25 Nov 2013 by technical library (as attachment 3). After receiving the manual list, TPE LM took it out from controlled CD manuals area, marked "for reference only", and put on LM manager's desk. This CD was presented during the audit on 18 Dec 2013 with a clear red mark of "for reference only". 5. The mentioned CD was scrapped in TPE station on 15 Jan 2014. Technical library sent a new CD which contains LM related cabin supplement document only (Supplement AMM, IPC & AWM in H4AMS101-Issue 2) on 14 Jan 2014. (as attachment 4) |  | 1. TN A320-00310 Rev 01 describes cabin modification affected documents which are using by pilot, cabin crew, system engineer and maintenance. Only maintenance related supplement manuals are chosen to published to AMU maintenance, including TPE. 2. TPE AMD are briefed to only use the maintenance manuals published by technical library. The disable manuals shall be scraped instead of marking "for reference only", to avoid the possibility of continuous use. Please refer to the internal letter (as attachment 5) for above requirement. 3. ED technical library has reviewed all manual control lists to ensure there is no missing manual, and he shall review the list before sending in the furture. | 2014-01-30
| 5 | A/196/13-6/6 | TPE Station Audit | QD |  | AMU BASE | Equipment, Tool & Material | TPE | N/A | 2 | 2759/DFSL/13 | 2013-12-30 | 2014-01-15 | OCS to CQD May Zhang | 2014-01-13 | Answered | 0240/DFSL/14 | 2014-01-28 | Accepted & Closed | [27 empty] | 0240/DFSL/14 | 2014-01-28 | N/A | N/A |  | Closed | MEPM 2.5.1 - Calibration of Tools and Equipment | During the audit, calibrated tools were sample checked. It was noted that a Tire Px Gauge, p/n: 14-6807-6011 s/n: 1424130207, had "date calibrated" remarked as "26-FEB'13" and "next due" remarked as "26-FEB'14" physically on the tool and on the "Station Calibration Tool" list (form no. PM L2.1.1-05). However, further checking with TPE storekeeper on AMASIS during the time of audit identified an "inspection" date of "20/05/2013" and a "deadline" date of "20/05/2014" within the AMASIS database. | 1. The wrong dates were input in the AMASIS by QCI . 2. Relevant QCI corrected the dates "Inspection Date=26/02/2013, Deadline Date=26/02/2014" in AMASIS according to Calibration Certificate of Tire Pressure Gauge. 3. Relevant QCI cross checked Inspection/Deadline Dates of all calibration tools according to their calibration certificates with AMASIS. All dates in AMASIS are correct. |  | Quality Control Manager briefed the requirement of MEPM 2.5.1 Para. 1.2 to all QCIs as attached Read & Sign record. To ensure Inspection/Deadline Date in AMASIS is correct, QCI is required to double check that monthly, according to calibration certificates in AMASIS. | 2014-01-31
Note on BA1: Close Open O+A=Open+Accepted O+E=Open+Extension A+W=answered and waiting A+R=answered and rejected
Note on P2: ENMWZN: Late letter from CQD
Note on P5: ENMWZN: Late rreply from ED
Note on P6: ENMWZN: Late rreply from ED

## Follow-up (hidden)
SN | CAR No. | Div/Sta. Affec. | Action2 | Letter Number | Issue date | Due date | Days Left | Status | Corrective Action-Proposed | Preventive Action-Proposed | Note | Action | Finding Level | Status | REG. No. | MODEL | Division/Station | Description | Clarification
1 | #REF! | #REF! | Waiting for action | 0140/DFSL/10 | 2011-01-18 | 2011-02-01 | -1121 | O+A |  |  |  | Answered | Level 1 | Open | N/A | N/A | QD | QD | CRS
2 | #REF! | #REF! | Waiting for action | 0140/DFSL/10 | 2011-01-18 | 2011-02-01 | -1121 | O+A |  |  |  | Extention | Level 2 | O+A | N/A | N/A | QD | QD | Maintenance Records
3 | #REF! | #REF! | Waiting for action | 0140/DFSL/10 | 2011-01-18 | 2011-02-01 | -1121 | O+A |  |  |  | Rejected | Level 3 | O+E | B-MAK | A319-132 | ED | ED | Maintenance Data
4 | #REF! | #REF! | Waiting for action | 0140/DFSL/10 | 2011-01-18 | 2011-02-01 | -1121 | O+A |  |  |  | Evidence | Level 3 | O+R | B-MAL | A319-132 | PPC | PPC | Training Records
5 | #REF! | #REF! | Answered | QD/AAC/11-022 | 2011-01-27 | N/A | N/A | O+A | To revise MEPM L 2.4.1 paragraph 14 to read that" ...... across the MAR 145.50 and; write the JMM number and the origin LAA approval Certificate number. " to meet the JMM requirement. | To revise MEPM L 2.4.1 paragraph 14 to read that" ...... across the MAR 145.50 and. write the JMM number and the origin LAA approval Certificate number. " to meet the JMM requirement. Notify relevant LM service Providers to follow the new procedures. |  | Closed |  | Closed | B-MAM | A319-132 | AMD | AMD | Marking
6 | #REF! | #REF! | Answered | QD/AAC/11-022 | 2011-01-27 | N/A | N/A | O+A | The MEL TR No.-2S/0 lA issue 01 has been issued and under approval. it will be inserted into MEL for reference. also, Alert to add UPK was accomplished. therefore. TN A320-00303 Rev. 01 is unnecessary to be sent out to Out Stations. | The TN master control list will be provided to Out Stations for their information whenever there is a TN relate to Out Stations. |  | Waiting for action |  | Evidence | B-MAN | A319-132 | MCC | MCC | Repair approval
7 | #REF! | #REF! | Answered | QD/AAC/11-022 | 2011-01-27 | N/A | N/A | O+A | To check the AMASIS database and if found the material is still within shelf life limit. To reissue Material Sticker for the mentioned AeroShell Grease 7 and Skydrol LD4 individual container. | 1. Request QCls to strictly follow the MEPM procedure 2.2.1 & 2.2.2 to ensure Material Sticker are issued and attached to relevant materials at individual container basis. 2. To revise MEPM procedure 2.3.2 to request LM Technicians to report any loss of sticker promptly to Material Recourses who will check the AMASIS database and if found the matetial is still within shelf life limit, to inform QCI to reissue the sticker. |  | Waiting for AACM answer |  |  | B-MAO | A319-132 | A320 | A320 | Remedial action
8 | #REF! | #REF! | Answered | QD/AAC/11-022 | 2011-01-27 | N/A | N/A | O+A | Material Resource on-site representative was requested to search for proper container in local for keeping the type of DG material. | The relevant staff was notified about this issue and called back from PEK to MFM for renew training on 20-Jan-20 11. |  | N/A |  |  | B-MAH | A320-232 | A300 | A300 | Feedback System
9 | #REF! | #REF! | Evidence | email from stephen | 2011-01-31 | N/A | N/A | Evidence |  |  |  | acceptable
10 | #REF! | #REF! | acceptable | email from stephen | 2011-01-31 | N/A | N/A | Closed
11 | #REF! | #REF! | Waiting for action | email from stephen | 2011-01-31 | 2011-02-14 | -1108 | O+A
12 | #REF! | #REF! | Evidence | email from stephen | 2011-01-31 | N/A | N/A | Evidence
15 | #REF! | #REF! | Answered | Answer to AACM | 2011-03-09 | N/A | N/A | O+A
16 | #REF! | #REF! | Answered | 0691/DFSL/11 | 2011-03-22 | N/A | N/A | Closed
9 | #REF! | #REF! | N/A | 0691/DFSL/11 | 2011-03-22 | N/A | N/A | Closed |  |  |  | acceptable
10 | #REF! | #REF! | N/A | 0691/DFSL/11 | 2011-03-22 | N/A | N/A | Closed
11 | #REF! | #REF! | N/A | 0691/DFSL/11 | 2011-03-22 | N/A | N/A | Closed
12 | #REF! | #REF! | N/A | email from stephen | 2011-01-31 | N/A | N/A | O+A
| #REF! | #REF! |  |  |  |  | -41696
-41696
-41696
-41696
-41696
-41696
Formulas:
Days Left = [Due date]-TODAY()
Note on C1: Department / Division affected.
Note on I1: Close Open O+A=Open+Accepted O+E=Open+Extension A+W=answered and waiting A+R=answered and rejected
Note on P3: OPEN+ANSWER
Note on P4: O+E=Open+Extension
Note on P5: Answered+Rejected

## 2014 Analysis
Report Month | No. of Audit | New Finding | Level 1 | Level 2 | Level 3 | Reoccurrence Finding
JAN | 1 | 1 | 0 | 1 | 0 | 1
FEB | 1 | 1 | 0 | 1 | 0 | 0
MAR | 2 | 7 | 0 | 3 | 4 | 0
APR | 1 | 2 | 0 | 2 | 0 | 0
MAY | 3 | 4 | 0 | 4 | 0 | 0
JUN | 2 | 9 | 0 | 9 | 0 | 1
JUL | 1 | 2 | 0 | 1 | 0 | 0
AUG
SEP
OCT
NOV
DEC
Total | 11 | 26 | 0 | 21 | 4 | 2
Area Concerned | Number of Finding
Maintenance Data | 2
Implementation of AC | 0
Training | 0
Technical Log | 0
Work Package | 0
Maintenance Records | 0
One Off Authorization | 0
AD control | 0
Storage | 0
Material Handling | 0
CMR Issuance | 0
C Check Personal Requirement | 0
SMS | 0
Maintenance Implementation | 0
DEPT/STN Concerned | QD | AMD | ED | MRD | CAMB
Maintenance Data | 0 | 1 | 0 | 0 | 0
Implementation of AC | 0 | 0 | 0 | 0 | 0
Equipment | 0 | 0 | 0 | 0 | 0
Training | 0 | 0 | 0 | 0 | 0
Technical Log | 0 | 0 | 0 | 0 | 0
Work Package | 0 | 0 | 0 | 0 | 0
Maintenance Records | 0 | 0 | 0 | 0 | 0
One Off Authorization | 0 | 0 | 0 | 0 | 0
AD control | 0 | 0 | 0 | 0 | 0
Storage | 0 | 0 | 0 | 0 | 0
Material Handling | 0 | 0 | 0 | 0 | 0
CMR Issuance | 0 | 0 | 0 | 0 | 0
C Check Personal Requirement | 0 | 0 | 0 | 0 | 0
Calibration | 0 | 0 | 0 | 0 | 0
Maintenance Implementation | 0 | 0 | 0 | 0 | 0
SMS | 0 | 0 | 0 | 0 | 0
Number of Finding | 0 | 1 | 0 | 0 | 0
DEPT/STN Concerned | QD | AMD | ED | MRD | CAMB | Total
Maintenance Data | 1 | 1 | 10 | 0 | 0 | 12
Maintenance Records | 0 | 1 | 3 | 0 | 0 | 4
Storage | 1 | 2 | 0 | 1 | 0 | 4
Work Package | 1 | 0 | 2 | 0 | 0 | 3
Equipment | 0 | 3 | 0 | 0 | 0 | 3
AD control | 0 | 0 | 2 | 0 | 0 | 2
Calibration | 0 | 1 | 0 | 1 | 0 | 2
A/C Cert | 1 | 0 | 1 | 0 | 0 | 2
Contract Management | 1 | 1 | 0 | 0 | 0 | 2
Implementation of AC | 0 | 0 | 1 | 0 | 0 | 1
Training | 1 | 0 | 0 | 0 | 0 | 1
Technical Log | 0 | 0 | 0 | 0 | 1 | 0
One Off Authorization | 1 | 0 | 0 | 0 | 0 | 1
Material Handling | 0 | 1 | 0 | 0 | 0 | 1
CMR Issuance | 1 | 0 | 0 | 0 | 0 | 1
C Check Personal Requirement | 0 | 0 | 1 | 0 | 0 | 1
Maintenance Implementation | 0 | 1 | 0 | 0 | 0 | 1
SMS | 1 | 0 | 0 | 0 | 0 | 1
Line Station Control | 1 | 0 | 0 | 0 | 0 | 1
Facility | 0 | 1 | 0 | 0 | 0 | 1
AMASIS | 0 | 1 | 0 | 0 | 0 | 1
Auditing | 1 | 0 | 0 | 0 | 0 | 1
Concession | 1 | 0 | 0 | 0 | 0 | 1
Procedure Conformity | 1 | 0 | 0 | 0 | 0 | 1