## Finding Control
Audit Type | Status | Reponsible QA | Follow-up Form | QAR No. | CAR/CAF No. | Audit Month | Audit Title /Follow up | Div/Sta. Affec.1 | Div/Sta. Affec.2 | Area Concerned | Location | Level | Letter Number | Reply Due Date | Letter No. | LetterDate | Result1 | Leter No. | LetterDate | Result2 | Leter No. | LetterDate | Result3 | Letter No. | LetterDate | Result4 | Leter No. | LetterDate | Result5 | Leter No. | LetterDate | Result6 | Leter No. | LetterDate | Result7 | Leter No. | LetterDate | Result8 | Leter No. | LetterDate | Result9 | Leter No. | LetterDate | Result10 | Leter No. | LetterDate | Result11 | The Last Letter Number | The Last-Issue date | The Alert Date | Final-Days Left | Result (before close) | Ref. | Finding | Corrective Action | CA Target Date | Preventive Action | PA Target Date | Internal Reject | Response Overdue (Internal) | Response Overdue (External) | Extension Applied | AACM/3rd Party Reject | CA/PA Extension Applied
Int' | Closed | Liu Feng | N/A' | 15-066 | CAF-15-156 | 2015-11-18 | A-Check Audit | ENM |  | Maintenance Data | MFM | 2 | e-mail to ED | 2015-12-15 | Reply from ED | 2015-12-11 | Accepted | E-mail from GMQA | 2016-02-17 | Extended | CMP11 and ED Letter received | 2016-05-26 | Closed | [24 empty] | CMP11 and ED Letter received | 2016-05-26 | Closed | N/A | Closed
3rd Party' | Closed | Neil | N/A' | N/A | A/12/16-1/1 | 2016-01-29 | B-MBA CoA Renewal | ED |  | Maintenance Responsibility | MFM | 2 | 0232/DFSL/16 | 2015-01-29 | OCS to CQD | 2016-02-11 |  | CQD/022/16 | 2016-02-16 |  | 0411/DFSL/16 | 2016-02-24 | Closed | [24 empty] | 0411/DFSL/16 | 2016-02-16 | N/A | N/A | Closed
3rd Party' | Closed | Neil | N/A' | N/A | A/13/16-1/1 | 2016-02-04 | B-MAN CoA Renewal | CPD | QD | COA Renewal | MFM | 2 | 0299/DFSL/16 | 2016-02-23 | OCS to CQD | 2016-02-22 |  | CQD/028/16 | 2016-02-23 |  | 0417/DFSL/16 | 2016-02-25 | Closed | [24 empty] | 0417/DFSL/16 | 2016-02-25 | N/A | N/A | Closed
Ext' | Closed | Ronald | N/A' | 16-003 | N/A | 2016-02-19 | HKG LS & Base Audit | [43 empty] | N/A | Closed
Int' | Closed | YU | N/A' | 16-007 | N/A | 2016-02-24 | KHH CPA Initial LS Audit | [43 empty] | N/A | Closed
Int' | Closed | YU | N/A' | 16-008 | CAF-16-013 | 2016-02-26 | TPE LS Audit | AMD |  | Material Handling | TPE | 2 | [36 empty] | 2016-03-31 | N/A | N/A | Closed
Ext' | Closed | Ronald | N/A' | 16-004 | N/A | 2016-02-26 | FUK Initial Audit | [43 empty] | N/A | Closed
3rd Party' | Closed | Neil | N/A' | N/A | A/32/16-1/1 | 2016-03-10 | B-MBB CoA Renewal | ED |  | Maintenance Procedure | MFM | 2 | 0520/DFSL/16 | 2016-03-24 | OCS to CQD | 2016-03-15 | CQD/039/16 | 2016-03-16 | Accepted | 061/DFSL/16 | 2016-03-21 | Closed | [25 empty] | 061/DFSL/16 | 2016-03-21 | N/A | N/A | Closed
Ext' | Closed | Xeno | N/A' | 16-009 | CAF-16-014 | 2016-03-18 | CTU Audit Base Maint. | Ameco CTU BM |  | Maintenance Data | CTU | 2 | Email to AMECO-CTU | 2016-04-12 | Email from AMECO-CTU | 2016-04-11 | Accepted | Email from AMECO-CTU | 2016-05-05 | Closed | [27 empty] | Email from AMECO-CTU | 2016-05-05 | N/A | N/A | Closed
Ext' | Closed | Xeno | N/A' | 16-009 | CAF-16-015 | 2016-03-18 | CTU Audit Base Maint. | Ameco CTU BM |  | Maintenance Procedure | CTU | 3 | Email to AMECO-CTU | 2016-04-12 | Email from AMECO-CTU | 2016-04-11 | Accepted | Email from AMECO-CTU | 2016-05-05 | Closed | [27 empty] | Email from AMECO-CTU | 2016-05-05 | N/A | N/A | Closed
Ext' | Closed | Xeno | N/A' | 16-010 | CAF-16-016 | 2016-03-18 | CTU Audit Line Maint. | Ameco CTU LM |  | Equipment, Tools and Materials | CTU | 2 | Email to AMECO-CTU | 2016-04-12 | Email from AMECO-CTU | 2016-04-11 | Accepted | Email from AMECO-CTU | 2016-05-05 | Closed | [27 empty] | Email from AMECO-CTU | 2016-05-05 | N/A | N/A | Closed
Ext' | Closed | Xeno | N/A' | 16-010 | CAF-16-017 | 2016-03-18 | CTU Audit Line Maint. | Ameco CTU LM |  | Equipment, Tools and Materials | CTU | 2 | Email to AMECO-CTU | 2016-04-12 | Email from AMECO-CTU | 2016-04-11 | Accepted | Email from AMECO-CTU | 2016-05-05 | Closed | [27 empty] | Email from AMECO-CTU | 2016-05-05 | N/A | N/A | Closed
Ext' | Closed | Xeno | N/A' | 16-010 | CAF-16-018 | 2016-03-18 | CTU Audit Line Maint. | CA-SW |  | Equipment, Tools and Materials | CTU | 2 | Email to AIR CHINA South West | 2016-04-12 | Email from Air China-SW | 2016-04-15 | Accepted | Verified by Xeno | 2016-06-20 | Closed | [27 empty] | Verified by Xeno | 2016-06-20 | N/A | N/A | Closed
Ext' | Closed | Xeno | N/A' | 16-010 | CAF-16-019 | 2016-03-18 | CTU Audit Line Maint. | CA-SW |  | Equipment, Tools and Materials | CTU | 2 | Email to AIR CHINA South West | 2016-04-12 | Email from Air China-SW | 2016-04-15 | Accepted | Verified by Xeno | 2016-06-20 | Closed | [27 empty] | Verified by Xeno | 2016-06-20 | N/A | N/A | Closed
Ext' | Closed | Xeno | N/A' | 16-010 | CAF-16-020 | 2016-03-18 | CTU Audit Line Maint. | CNAF- CTU |  | Personnel Tranining | CTU | 2 | Email to CNAF-CTU | 2016-04-12 | Email from CNAF-CTU | 2016-04-11 | Accepted | [31 empty] | 2016-03-30 | N/A | N/A | Closed
Ext' | Closed | Xeno | N/A' | 16-010 | CAF-16-021 | 2016-03-18 | CTU Audit Line Maint. | CNAF- CTU |  | Manual Control | CTU | 2 | Email to CNAF-CTU | 2016-04-12 | Email from CNAF-CTU | 2016-04-11 | Accepted | [31 empty] | 2016-03-30 | N/A | N/A | Closed
3rd Party' | Closed | Simon | N/A' | N/A | A/46/16-1/4 | 2016-03-23 | MAR-145 Phase I Audit 2016 | AMD |  | Equipment, Tools and Materials | MFM | 2 | 0622/DFSL/16 | 2016-04-06 | OCS to CQD | 2016-04-05 |  | 0744/DFSL/16 | 2016-04-11 | Closed | [27 empty] | 0774/DFSL/16 | 2016-04-11 | N/A | N/A | Closed
3rd Party' | closed | Simon | N/A' | N/A | A/46/16-2/4 | 2016-03-23 | MAR-145 Phase I Audit 2016 | QD |  | Quality System | MFM | 2 | 0622/DFSL/16 | 2016-04-06 | OCS to CQD | 2016-04-05 |  | 0744/DFSL/16 | 2016-04-11 | Closed | [27 empty] | 0774/DFSL/16 | 2016-04-11 | N/A | N/A | Closed
3rd Party' | Closed | Simon | N/A' | N/A | A/46/16-3/4 | 2016-03-23 | MAR-145 Phase I Audit 2016 | AMD |  | Facility | MFM | 3 | 0622/DFSL/16 | 2016-04-06 | OCS to CQD | 2016-04-05 |  | 0744/DFSL/16 | 2016-04-11 | Closed | [27 empty] | 0774/DFSL/16 | 2016-04-11 | N/A | N/A | Closed
3rd Party' | Closed | Simon | N/A' | N/A | A/46/16-4/4 | 2016-03-23 | MAR-145 Phase I Audit 2016 | QD |  | Internal Procedure | MFM | 3 | 0622/DFSL/16 | 2016-04-06 | OCS to CQD | 2016-04-05 |  | 0744/DFSL/16 | 2016-04-11 | Closed | [27 empty] | 0774/DFSL/16 | 2016-04-11 | N/A | N/A | Closed
Ext' | Closed | Xeno | N/A' | 16-011 | CAF-16-022 | 2016-04-01 | HGH Audit | Ameco HGH |  | Training | HGH | 2 | Email to AMECO-HGH | 2016-04-06 | Email from AMECO-HGH | 2016-04-18 | Accepted | Email from AMECO-HGH | 2016-04-30 | Closed | Email to AMECO-HGH | 2016-05-06 | Closed | [24 empty] | Email to AMECO-HGH |  | N/A | N/A | Closed
Ext' | Closed | Xeno | N/A' | 16-011 | CAF-16-023 | 2016-04-01 | HGH Audit | Ameco HGH |  | Maitenance Records | HGH | 2 | Email to AMECO-HGH | 2016-04-06 | Email from AMECO-HGH | 2016-04-18 | Accepted | Email from AMECO-HGH | 2016-04-30 | Open | Email to AMECO-HGH | 2016-05-06 | Open | [24 empty] | Email to AMECO-HGH | 2016-05-06 | N/A | N/A | Open
Ext' | Closed | Xeno | N/A' | 16-011 | CAF-16-024 | 2016-04-01 | HGH Audit | Ameco HGH |  | Contract Compliance (SLA) | HGH | 2 | Email to AMECO-HGH | 2016-04-06 | Email from AMECO-HGH | 2016-04-18 | Accepted | Email from AMECO-HGH | 2016-04-30 | Closed | Email to AMECO-HGH | 2016-05-06 | Closed | [24 empty] | Email to AMECO-HGH | 2016-05-06 | N/A | N/A | Closed
Int' | Closed | Neil | N/A' | 16-013 | CAF-16-028 | 2016-04-07 | Component Capability C20 | AMD |  | Material Management | MFM | 2 | Email to AMD | 2016-04-08 | Reply from AMD | 2016-04-18 | Accepted | Verified by Simon | 2016-05-11 | Accepted | [27 empty] | Verified by Simon | 2016-05-11 | N/A | N/A | Closed
Int' | Closed | Neil | N/A' | 16-013 | CAF-16-029 | 2016-04-07 | Component Capability C20 | AMD |  | Material Management | MFM | 2 | Email to AMD | 2016-04-08 | Reply from AMD | 2016-04-18 | Accepted | Verified by Simon | 2016-05-11 | Accepted | [27 empty] | Verified by Simon | 2016-05-11 | N/A | N/A | Closed
3rd Party' | Open | Simon | N/A' | N/A | 2016-HA-SJ-AM-MNT-F-01 | 2016-04-01 | Air China Safety Inspection | ENM |  | Management System | MFM | 2 | Email to VPEM and ENM GMs |  | Reply from GMs | 2016-06-03 | [31 empty] | Email from GMs | 2016-06-03 | 2016-12-10 | 59 | Open
3rd Party' | Closed | Simon | N/A' | N/A | 2016-HA-SJ-AM-MNT-F-02 | 2016-04-01 | Air China Safety Inspection | ED | QD | Maintenance Program | MFM | 2 | Email to VPEM and ENM GMs |  | Reply from ED | 2016-05-20 | Accepted | [30 empty] | Email from ED | 2016-05-20 | N/A | N/A | Closed
3rd Party' | Closed | Simon | N/A' | N/A | 2016-HA-SJ-AM-MNT-F-03 | 2016-04-01 | Air China Safety Inspection | ED | AMD | Maintenance record | MFM | 2 | Email to VPEM and ENM GMs | [36 empty] | N/A | N/A | Closed
3rd Party' | Closed | Simon | N/A' | N/A | 2016-HA-SJ-AM-MNT-F-04 | 2016-04-01 | Air China Safety Inspection | AMD | MCD | Materials | MFM | 2 | Email to VPEM and ENM GMs |  | Verified by Neil | 2016-04-20 | Accepted | [31 empty] | 2016-04-18 | N/A | N/A | Closed
3rd Party' | Closed | Simon | N/A' | N/A | 2016-HA-SJ-AM-MNT-F-05 | 2016-04-01 | Air China Safety Inspection | MRD | QD | Equipment, Tools and Materials | MFM | 2 | Email to VPEM and ENM GMs |  | Reply from MRD | 2016-05-05 |  | Email to MRD | 2016-05-06 |  | Email from MRD | 2016-05-18 | 1/3 & 2/3 related to MRD are closed | Email from QC | 2016-05-30 | Accepted, additional action needed | [21 empty] | Email from QC | 2016-05-30 | N/A | N/A | Closed
3rd Party' | Open | Simon | N/A' | N/A | 2016-HA-SJ-AM-MNT-OB-01 | 2016-04-01 | Air China Safety Inspection | ED |  | Maintenance Instructions | MFM | 3 | Email to VPEM and ENM GMs | [36 empty] | 2017-10-30 | 383 | Open
3rd Party' | Closed | Simon | N/A' | N/A | 2016-HA-SJ-AM-MNT-OB-02 | 2016-04-01 | Air China Safety Inspection | MRD | AMD/QD | Materials | MFM | 3 | Email to VPEM and ENM GMs |  | Revise MEPM 2.2.1 & 2.3.2 (MARF-16-022/023) | 2016-05-13 | Closed | [30 empty] | Verified by Simon | 2016-05-13 | N/A | N/A | Closed
3rd Party' | Open | Simon | N/A' | N/A | 2016-HA-SJ-AM-MNT-OB-03 | 2016-04-01 | Air China Safety Inspection | ED | QD | Maintenance record | MFM | 3 | Email to VPEM and ENM GMs |  | Email from QC | 2016-05-30 | Accepted and additional action needed | [30 empty] | Email from QC | 2016-05-30 | 2017-10-30 | 383 | Open
3rd Party' | Closed | Simon | N/A' | N/A | 2016-HA-SJ-GH-ORG-F-01 | 2016-04-01 | Air China Safety Inspection | ENM |  | Management System | MFM | 2 | Email to VPEM and ENM GMs | [36 empty] | N/A | N/A | Closed
3rd Party' | Closed | Simon | N/A' | N/A | 2016-HA-SJ-GH-ORG-F-02 | 2016-04-01 | Air China Safety Inspection | ED | ENM | SMS | MFM | 2 | Email to VPEM and ENM GMs | [36 empty] | N/A | N/A | Closed
3rd Party' | Closed | Simon | N/A' | N/A | 2016-HA-SJ-GH-ORG-F-03 | 2016-04-01 | Air China Safety Inspection | QD |  | SMS | MFM | 2 | Email to VPEM and ENM GMs | [36 empty] | N/A | N/A | Closed
3rd Party' | Closed | Simon | N/A' | N/A | 2016-HA-SJ-GH-ORG-F-05 | 2016-04-01 | Air China Safety Inspection | QD |  | SMS | MFM | 2 | Email to VPEM and ENM GMs |  | email to ASD | 2016-08-23 | [33 empty] | N/A | N/A | Closed
Ext' | Closed | Neil | N/A' | 16-015 | CAF-16-031 | 2016-04-12 | NKG LM Audit | NKG LM |  | Maintenance Data | NKG | 2 | Email to NKG LM | 2016-05-03 | email from NKG | 2016-04-29 |  | email to NKG | 2016-05-03 |  | email from NKG | 2016-05-06 | Wait for Training & Inspection Record | email from NKG | 2016-05-13 | Accepted | [22 empty] | 2016-05-13 | N/A | N/A | Closed
Ext' | Closed | Neil | N/A' | 16-015 | CAF-16-032 | 2016-04-12 | NKG LM Audit | NKG LM |  | Maintenance Procedure | NKG | 2 | Email to NKG LM | 2016-05-03 | email from NKG | 2016-04-29 |  | email to NKG | 2016-05-03 |  | email from NKG | 2016-05-06 | Accepted | [25 empty] | 2016-05-06 | N/A | N/A | Closed
Ext' | Closed | Neil | N/A' | 16-015 | CAF-16-033 | 2016-04-12 | NKG LM Audit | NKG LM |  | Maintenance Procedure | NKG | 2 | Email to NKG LM | 2016-05-03 | email from NKG | 2016-04-29 |  | email to NKG | 2016-05-03 |  | email from NKG | 2016-05-06 | Wait for QN Training Record | email from NKG | 2016-05-13 | Accepted | [22 empty] | 2016-05-13 | N/A | N/A | Closed
3rd Party' | Closed | Neil | N/A' | N/A | A/42/16-1/2 | 2016-04-29 | AACM BKK Audit | BKK |  | Maintenance Procedure | BKK | 2 | Email to BKK LM | 2016-05-13 | OCS to CQD | 2016-05-18 |  | CQD/069/16 | 2016-05-18 |  | 1039/DFSL/16 | 2016-06-06 | Closed | [24 empty] | 1039/DFSL/16 | 2016-06-06 | N/A | N/A | Closed
3rd Party' | Open | Neil | N/A' | N/A | A/42/16-2/2 | 2016-04-29 | AACM BKK Audit | BKK |  | Training | BKK | 2 | Email to BKK LM | 2016-05-13 | OCS to CQD | 2016-05-18 |  | CQD/069/16 | 2016-05-18 |  | 1039/DFSL/16 | 2016-06-06 | Evidence | email from BKK | 2016-06-15 | Accepted | email to CQD | 2016-06-16 |  | CQD/089/16 | 2016-06-20 | [16 empty] | CQD/089/16 | 2016-06-20 | N/A | N/A | Open
Ext' | Closed | Xeno | N/A' | 16-019 | CAF-16-044 | 2016-04-28 | BKK Station Audit | Thai Airways |  | Safety Cone | BKK | 2 | Email to BKK LM | 2016-05-20 | [35 empty] | N/A | N/A | Closed
Ext' | Closed | Xeno | N/A' | 16-019 | CAF-16-045 | 2016-04-28 | BKK Station Audit | Thai Airways |  | Maintenance record | BKK | 2 | Email to BKK LM | 2016-05-20 | [35 empty] | N/A | N/A | Closed
Ext' | Open | Xeno | N/A' | 16-019 | CAF-16-046 | 2016-04-28 | BKK Station Audit | Thai Airways |  | SMS | BKK | 3 | Email to BKK LM | 2016-05-20 | [34 empty] | 2016-10-12 | 2016-12-22 | 71 | Accepted
Ext' | Closed | Xeno | N/A' | 16-019 | CAF-16-047 | 2016-04-28 | BKK Station Audit | Thai Airways |  | Internal Audit | BKK | 3 | Email to BKK LM | 2016-05-20 | [35 empty] | N/A | N/A | Closed
Ext' | Closed | Xeno | N/A' | 16-019 | CAF-16-048 | 2016-04-28 | BKK Station Audit | Thai Airways |  | GSE (Shear Pin Installation) | BKK | 2 | Email to BKK LM | 2016-05-20 | [35 empty] | N/A | N/A | Closed
Ext' | Closed | Xeno | N/A' | 16-019 | CAF-16-049 | 2016-04-28 | BKK Station Audit | Thai Airways |  | GSE (Beacon Light) | BKK | 2 | Email to BKK LM | 2016-05-20 | [35 empty] | N/A | N/A | Closed
Ext' | Closed | Neil | N/A' | 16-025 | N/A | 2016-05-11 | SHA Spring Airlines Audit |  |  |  | SHA | [38 empty] | N/A | N/A | Closed
3rd Party' | Closed | Neil | N/A' | N/A | A/88/16-1/2 | 2016-05-20 | KIX Station Audit | KIX JALEC |  | Maintenance Procedure | KIX | 2 | Email to KIX | 2016-05-30 | OCS to CQD | 2016-06-03 |  | CQD/080/16 | 2016-06-06 |  | AACM 1181/DFSL/16 | 2016-06-13 | Closed | [24 empty] | AACM 1181/DFSL/16 | 2016-06-13 | N/A | N/A | Closed
3rd Party' | Closed | Neil | N/A' | N/A | A/88/16-2/2 | 2016-05-20 | KIX Station Audit | QD |  | Authorization | KIX | 2 |  |  | OCS to CQD | 2016-06-03 |  | CQD/080/16 | 2016-06-06 |  | AACM 1181/DFSL/16 | 2016-06-13 | Closed | confirmed reminder works | [23 empty] | AACM 1181/DFSL/16 | 2016-07-06 | N/A | N/A | Closed
3rd Party' | Closed | Simon | N/A' | N/A | N/A | 2016-05-12 | Self Inspection Asked by Air China | QD |  | Maintenance Procedure | MFM |  | Email to ASD | [34 empty] | Email to ASD | 2016-08-27 | N/A | N/A | Closed
3rd Party' | Closed | Simon | N/A' | N/A | N/A | 2016-05-12 | Self Inspection Asked by Air China | AMD |  | Equipment, Tools and Material | MFM |  |  |  | Reply from AMD | 2016-07-29 | [32 empty] | 2016-07-29 | N/A | N/A | Open
Int' | Closed | Liu Feng | N/A' | 16-028 | CAF-16-054 | 2016-05-27 | MNT 1 2 3 4 Audit | QD |  | Maintenance Procedure | MFM | 2 | email to Div | 2016-06-17 | Reply from QD | 2016-06-15 |  | email from Ronald | 2016-06-20 | closed | [30 empty] | N/A | Closed
Int' | Closed | Liu Feng | N/A' | 16-028 | CAF-16-055 | 2016-05-27 | MNT 1 2 3 4 Audit | QD |  | Maintenance Procedure | MFM | 2 | email to Div | 2016-06-17 | Reply from QD | 2016-06-15 |  | all supporting done | 2016-07-11 | closed | [29 empty] | N/A | N/A | Closed
Int' | Closed | Liu Feng | N/A' | 16-028 | CAF-16-056 | 2016-05-27 | MNT 1 2 3 4 Audit | ED |  | Maintenance Record | MFM | 2 | email to Div | 2016-06-17 | Reply from ED | 2016-06-15 |  | CAF from ED |  | closed | [29 empty] | N/A | N/A | Closed
Int' | Open | Liu Feng | N/A' | 16-028 | CAF-16-057 | 2016-05-27 | MNT 1 2 3 4 Audit | MRD |  | Equipment, Tools and Materials | MFM | 2 | email to Div | 2016-06-17 | Reply from MRD | 2016-06-16 | Accepted | Extension Request | 2016-08-31 | Extended | [29 empty] | 2016-11-23 | 42 | Open
Int' | Closed | Neil | N/A' | 16-028 | CAF-16-058 | 2016-05-27 | MNT 1 2 3 4 Audit | ED |  | Maintenance Data | MFM | 2 | email to Div | 2016-06-01 | Reply from ED | 2016-06-15 | [32 empty] | 2016-06-17 | N/A | N/A | Closed
Int' | Closed | Neil | N/A' | 16-028 | CAF-16-059 | 2016-05-27 | MNT 1 2 3 4 Audit | ED |  | Maintenance Program | MFM | 2 | email to Div | 2016-06-01 | Reply from ED | 2016-06-15 | [32 empty] | 2016-06-17 | N/A | N/A | Closed
Int' | Closed | Neil | N/A' | 16-028 | CAF-16-060 | 2016-05-27 | MNT 1 2 3 4 Audit | ED/MRD | QD | AD | MFM | 2 | email to Div | 2016-06-01 | Reply from ED | 2016-06-15 |  | Reply from MRD | 2016-06-15 |  | Reply from QD | 2016-06-17 | [26 empty] | 2016-06-17 | N/A | N/A | Closed
Int' | Closed | Neil | N/A' | 16-028 | CAF-16-061 | 2016-05-27 | MNT 1 2 3 4 Audit | QD |  | Maintenance Program | MFM | 2 | email to Div | 2016-06-01 | Reply from QD | 2016-06-13 | [32 empty] | 2016-06-17 | N/A | N/A | Closed
Int' | Closed | Neil | N/A' | 16-028 | CAF-16-062 | 2016-05-27 | MNT 1 2 3 4 Audit | ED |  | Maintenance Procedure | MFM | 2 | email to Div | 2016-06-01 | Reply from ED | 2016-06-15 | [32 empty] | 2016-06-17 | N/A | N/A | Closed
Int' | Closed | Neil | N/A' | 16-028 | CAF-16-063 | 2016-05-27 | MNT 1 2 3 4 Audit | ED |  | AD | MFM | 2 | email to Div | 2016-06-01 | Reply from ED | 2016-06-15 | [32 empty] | 2016-06-17 | N/A | N/A | Closed
Int' | Closed | Neil | N/A' | 16-028 | CAF-16-064 | 2016-05-27 | MNT 1 2 3 4 Audit | ED |  | AD | MFM | 2 | email to Div | 2016-06-01 | Reply from ED | 2016-06-15 | [32 empty] | 2016-06-17 | N/A | N/A | Closed
Int' | Closed | Xeno | N/A' | 16-028 | CAF-16-065 | 2016-05-27 | MNT 1 2 3 4 Audit | ED |  |  | MFM | 2 | email to Div | 2016-06-01 | [35 empty] | N/A | N/A | Closed
Int' | Closed | Xeno | N/A' | 16-028 | CAF-16-066 | 2016-05-27 | MNT 1 2 3 4 Audit | ED |  |  | MFM | 2 | email to Div | 2016-06-01 | [35 empty] | N/A | N/A | Closed
Int' | Closed | Xeno | N/A' | 16-028 | CAF-16-067 | 2016-05-27 | MNT 1 2 3 4 Audit | ED |  |  | MFM | 2 | email to Div | 2016-06-01 | [35 empty] | N/A | N/A | Closed
Int' | Closed | Xeno | N/A' | 16-028 | CAF-16-068 | 2016-05-27 | MNT 1 2 3 4 Audit | AMD |  |  | MFM | 2 | email to Div | 2016-06-01 | [35 empty] | N/A | N/A | Closed
Int' | Closed | Xeno | N/A' | 16-028 | CAF-16-069 | 2016-05-27 | MNT 1 2 3 4 Audit | ED |  |  | MFM | 2 | email to Div | 2016-06-01 | [35 empty] | N/A | N/A | Closed
Int' | Closed | Xeno | N/A' | 16-028 | CAF-16-070 | 2016-05-27 | MNT 1 2 3 4 Audit | MRD |  |  | MFM | 2 | email to Div | 2016-06-01 | [35 empty] | N/A | N/A | Closed
Int' | Closed | Xeno | N/A' | 16-028 | CAF-16-071 | 2016-05-27 | MNT 1 2 3 4 Audit | QD |  |  | MFM | 2 | email to Div | 2016-06-01 | [35 empty] | N/A | N/A | Closed
Int' | Closed | Ronald | N/A' | 16-028 | CAF-16-072 | 2016-05-27 | MNT 1 2 3 4 Audit | QD |  |  | MFM | 2 | email to Div | 2016-06-01 | [34 empty] | 2016-06-17 | N/A | N/A | Closed
Int' | Closed | Ronald | N/A' | 16-028 | CAF-16-073 | 2016-05-27 | MNT 1 2 3 4 Audit | QD |  |  | MFM | 2 | email to Div | 2016-06-01 | [34 empty] | 2016-06-17 | N/A | N/A | Closed
Int' | Closed | Ronald | N/A' | 16-028 | CAF-16-074 | 2016-05-27 | MNT 1 2 3 4 Audit | QD |  |  | MFM | 3 | email to Div | 2016-06-01 | [34 empty] | 2016-06-17 | N/A | N/A | Closed
Int' | Closed | Ronald | N/A' | 16-028 | CAF-16-075 | 2016-05-27 | MNT 1 2 3 4 Audit | QD |  |  | MFM | 2 | email to Div | 2016-06-01 | [34 empty] | 2016-06-17 | N/A | N/A | Closed
Int' | Closed | Ronald | N/A' | 16-028 | CAF-16-076 | 2016-05-27 | MNT 1 2 3 4 Audit | QD |  |  | MFM | 2 | email to Div | 2016-06-01 | [34 empty] | 2016-06-17 | N/A | N/A | Closed
Int' | Closed | Ronald | N/A' | 16-028 | CAF-16-077 | 2016-05-27 | MNT 1 2 3 4 Audit | MRD |  |  | MFM | 2 | email to Div | 2016-06-01 | [34 empty] | 2016-06-17 | N/A | N/A | Closed
Int' | Closed | Ronald | N/A' | 16-028 | CAF-16-078 | 2016-05-27 | MNT 1 2 3 4 Audit | MRD |  |  | MFM | 2 | email to Div | 2016-06-01 | [35 empty] | N/A | N/A | Closed
Ext' | Closed | Liu Feng | N/A' | 16-031 | CAF-16-091 | 2016-05-31 | NGB Station Audit | NGB |  | GSE | NGB | 2 | email to NGB | 2016-06-17 | email to NGB | 2016-06-08 |  | email from NGB | 2016-06-17 | Accepted | [29 empty] | N/A | N/A | Closed
Ext' | Closed | Liu Feng | N/A' | 16-031 | CAF-16-092 | 2016-05-31 | NGB Station Audit | NGB |  | GSE | NGB | 2 | email to NGB | 2016-06-17 | email to NGB | 2016-06-08 |  | email from NGB | 2016-06-17 | Accepted |  |  |  | email from NGB | 2016-07-12 | closed | [23 empty] | N/A | N/A | Closed
Ext' | Closed | Liu Feng | N/A' | 16-031 | CAF-16-093 | 2016-05-31 | NGB Station Audit | NGB |  | De-/anti-icing | NGB | 2 | email to NGB | 2016-06-17 | email to NGB | 2016-06-08 |  | email from NGB | 2016-06-17 | Accepted | email from NGB | 2016-08-22 | Closed | [26 empty] | N/A | N/A | Closed
Ext' | Closed | Liu Feng | N/A' | 16-031 | CAF-16-094 | 2016-05-31 | NGB Station Audit | NGB |  | Tools | NGB | 2 | email to NGB | 2016-06-17 | email to NGB | 2016-06-08 |  | email from NGB | 2016-06-17 | Accepted | [29 empty] | n/a | N/A | Closed
Ext' | Closed | Liu Feng | N/A' | 16-031 | CAF-16-095 | 2016-05-31 | NGB Station Audit | NGB |  | De-/anti-icing | NGB | 3 | email to NGB | 2016-06-17 | email to NGB | 2016-06-08 |  | email from NGB | 2016-06-17 | Accepted | email from NGB | 2016-08-22 | Closed | [26 empty] | N/A | N/A | Closed
Ext' | Closed | Liu Feng | N/A' | 16-031 | CAF-16-096 | 2016-05-31 | NGB Station Audit | NGB |  | H2O | NGB | 3 | email to NGB | 2016-06-17 | email to NGB | 2016-06-08 |  | email from NGB | 2016-06-17 | Accepted | [29 empty] | N/A | N/A | Closed
Ext' | Closed | Liu Feng | N/A' | 16-036 | CAF-16-101 | 2016-06-23 | CKG Station Audit | CKG |  | GSE | CKG | 2 | email to CKG | 2016-06-30 | email from CKG | 2016-07-13 | Accepted | email from CKG | 2016-07-20 | Closed | [29 empty] | N/A | N/A | Closed
Int' | Closed | Neil | N/A' | 16-038 | CAF-16-103 | 2016-06-28 | CGO Station Audit | CGO |  | H2O | CGO | 2 | email to CGO | 2016-07-07 | email to CGO | 2016-07-07 |  | email from CGO | 2016-07-15 | Accepted | email from CGO | 2016-08-12 | Closed | [25 empty] | 2016-08-12 | N/A | N/A | Closed
Ext' | Closed | Liu Feng | N/A' | 16-041 | CAF-16-105 | 2016-07-04 | KWE Station Audit | KWE |  | Tools | KWE | 2 | email to KWE | 2016-07-14 | email from AMECO-KWE | 2016-07-19 | Accept |  | 2016-09-01 | Extended | email to KWE | 2016-09-03 | Closed | [26 empty] | N/A | N/A | Closed
Ext' | Closed | Liu Feng | N/A' | 16-041 | CAF-16-106 | 2016-07-04 | KWE Station Audit | KWE |  | Materials | KWE | 2 | email to KWE | 2016-07-14 | email from AMECO-KWE | 2016-07-19 | Accept |  | 2016-09-01 | Extended | email to KWE | 2016-09-03 | Closed | [26 empty] | N/A | N/A | Closed
Ext' | Closed | Liu Feng | N/A' | 16-041 | CAF-16-107 | 2016-07-06 | KWE Station Audit | KWE |  | GSE | KWE | 2 | email to KWE | 2016-07-14 | email from AMECO-KWE | 2016-07-19 | Accept |  | 2016-09-01 | Extended | email to KWE | 2016-09-03 | Closed | [26 empty] | N/A | N/A | Closed
Ext' | Closed | Liu Feng | N/A' | 16-041 | CAF-16-108 | 2016-07-06 | KWE Station Audit | KWE |  | Potable Water | KWE | 2 | email to KWE | 2016-07-15 | phone to KWE | 2016-07-29 |  | email reply from KWE | 2016-08-06 | no acceptable | email to KWE | 2016-08-06 | no response | SMS to KWE | 2016-08-06 | no response | SMS to KWE | 2016-08-08 | no response | email to GMQA | 2016-08-09 | Apply to extend | email to GMQA | 2016-08-18 | Apply to extend | email from KWE | 2016-08-25 | Not acceptable | email and call to KWE | 2016-08-31 | extension | SMS from KWE | 2016-09-08 | extension | email from KWE | 2016-09-12 | Closed |  |  | N/A | N/A | Closed
Ext' | Closed | Liu Feng | N/A' | 16-041 | CAF-16-109 | 2016-07-06 | KWE Station Audit | KWE |  | Potable Water | KWE | 2 | email to KWE | 2016-07-15 | phone to KWE | 2016-07-29 | [16 empty] | email to GMQA | 2016-08-19 | Apply to extend | email from KWE | 2016-08-25 | Not acceptable | email and call to KWE | 2016-08-31 | extension | SMS from KWE | 2016-09-08 | extension | email from KWE | 2016-09-12 | Closed |  |  | N/A | N/A | Closed
3rd Party' | Closed | Xeno | N/A' | N/A | A/103/16-1/3 | 2016-07-22 | MAR-145 Phase II Audit 2016 | ED |  | Reliability | MFM | 2 | email to ED | 2016-07-21 | OCS to CQD | 2016-07-29 |  | CQD/103/16 | 2016-08-01 |  | 1513/DFSL/16 | 2016-08-03 | Closed | [26 empty] | N/A | N/A | Closed
3rd Party' | Closed | Xeno | N/A' | N/A | A/103/16-2/3 | 2016-07-22 | MAR-145 Phase II Audit 2016 | QD |  | Maintenance Data | MFM | 2 | email to QD | 2016-07-21 | OCS to CQD | 2016-07-29 |  | CQD/103/16 | 2016-08-01 |  | 1513/DFSL/16 | 2016-08-03 | Evidence | 1625/DFSL/16 | 2016-08-17 | Closed | [22 empty] | 2016-08-17 | N/A | N/A | Closed
3rd Party' | Closed | Xeno | N/A' | N/A | A/103/16-3/3 | 2016-07-22 | MAR-145 Phase II Audit 2016 | ED |  | Reliability | MFM | 2 | email to ED | 2016-07-21 | OCS to CQD | 2016-07-29 |  | CQD/103/16 | 2016-08-01 |  | 1513/DFSL/16 | 2016-08-03 | Evidence | 1625/DFSL/16 | 2016-08-17 | Evidence | email to CQD | 2016-09-21 | Evidence | CQD/113/16 | 2016-09-21 | Evidence | 1942/DFSL/16 | 2016-09-30 | Closed | [13 empty] | 2016-09-30 | N/A | N/A | Closed
Ext' | Closed | Simon | N/A' | 16-044 | CAF-16-114 | 2016-07-18 | TSN Station Audit | TSN |  | Maintenance Data | TSN | 2 | email to TSN | 2016-08-01 | Reply from Ameco-TSN | 2016-08-10 | Accepted and additional action needed | Email From TSN | 2016-08-22 | Closed | [28 empty] | 2016-08-22 | N/A | N/A | Closed
Ext' | Closed | Simon | N/A' | 16-044 | CAF-16-115 | 2016-07-18 | TSN Station Audit | TSN |  | Tools | TSN | 2 | email to TSN | 2016-08-01 | Reply from Ameco-TSN | 2016-08-10 | Closed | [31 empty] | 2016-08-12 | N/A | N/A | Closed
Ext' | Closed | Simon | N/A' | 16-044 | CAF-16-116 | 2016-07-18 | TSN Station Audit | TSN |  | GSE | TSN | 2 | email to TSN | 2016-08-01 | Reply from TBIA | 2016-08-10 | Closed | [31 empty] | 2016-08-12 | N/A | N/A | Closed
Ext' | Closed | Simon | N/A' | 16-044 | CAF-16-117 | 2016-07-18 | TSN Station Audit | TSN |  | Patable Water | TSN | 2 | email to TSN | 2016-08-01 | Reply from TBIA | 2016-08-10 | Closed | [31 empty] | 2016-08-12 | N/A | N/A | Closed
Ext' | Open | Simon | N/A' | 16-044 | CAF-16-118 | 2016-07-18 | TSN Station Audit | TSN |  | Patable Water | TSN | 2 | email to TSN | 2016-08-01 | Reply from TBIA | 2016-08-10 | [31 empty] | Extension | 2016-09-27 | 2016-10-26 | 14 | Open
Int' | Closed | YU | N/A' | 16-043 | CAF-16-110 | 2016-07-22 | Cross Audit-ORG | CQD |  | Corporate safety policy | MFM | 2 | email to CQD | 2016-07-30 | CQD Asked to extend | 2016-08-12 | Extended | email from CQD | 2016-08-23 | CAP accepted | [29 empty] | N/A | N/A | Closed
Int' | Open | YU | N/A' | 16-043 | CAF-16-111 | 2016-07-22 | Cross Audit-ORG | CQD |  | Delegation of duties | MFM | 3 | email to CQD | 2016-07-30 | CQD Asked to extend | 2016-08-12 | Extended | email from CQD | 2016-08-23 | CAP accepted | email from CQD | 2016-09-26 | extend to 20-Oct-2016 | [24 empty] | Extension |  | 2016-10-20 | 8 | Open
Int' | Closed | YU | N/A' | 16-043 | CAF-16-112 | 2016-07-22 | Cross Audit-ORG | CQD |  | Quality Management Evaluation | MFM | 3 | email to CQD | 2016-07-30 | email from CQD | 2016-08-03 | Closed | [32 empty] | N/A | N/A | Closed
Int' | Closed | Simon | N/A' | 16-046 | N/A | 2016-07-28 | Cross Audit-GRH | CSD
Int' | Closed | Simon | N/A' | 16-047 | N/A | 2016-07-28 | Cross Audit-CGO | CSD
3rd Party' | Closed | Ronald | N/A' | N/A' | A/110/16-1/1 | 2016-08-12 | B-MAL ASL Renewal | QD |  | Aircraft Station License | MFM | 2 | emai to QD | 2016-08-29 |  | 2016-08-12 |  | 1809/DFSL/16 | 2016-09-12 | Closed | [28 empty] | 2016-09-12 | N/A | N/A | Closed
3rd Party' | Open | Neil | N/A' | N/A' | A/125/16-1/3 | 2016-09-14 | AACM TPE Audit | TPE | MRD | Materials | TPE | 2 | 1863/DFSL/16 | 2016-09-21 | OCS to CQD | 2016-09-30 | [32 empty] | 2016-09-30 | 2016-10-31 | 19 | Open
3rd Party' | Open | Neil | N/A' | N/A' | A/125/16-3/3 | 2016-09-14 | AACM TPE Audit | ED |  | Maintenance Data | TPE | 2 | 1863/DFSL/16 | 2016-09-21 | OCS to CQD | 2016-09-30 | [33 empty] | N/A | N/A | Open
Ext' | Closed | Ronald | N/A' | 16-053 | N/A | 2016-09-22 | Ameco Beijing A Check | PEK
Formulas:
Final-Days Left = [The Alert Date]-TODAY()
Note on B1: Close Open O+A=Open+Accepted O+E=Open+Extension A+W=answered and waiting A+R=answered and rejected

## Follow-up (hidden)
SN | CAR No. | Div/Sta. Affec. | Action2 | Letter Number | Issue date | Due date | Days Left | Status | Corrective Action-Proposed | Preventive Action-Proposed | Note | Action | Finding Level | Status | REG. No. | MODEL | Division/Station | Description | Clarification
1899-12-31 | #REF! | #REF! | Waiting for action | 0140/DFSL/10 | 2011-01-18 | 2011-02-01 | -2080 | O+A |  |  |  | Answered | Level 1 | Open | N/A | N/A | QD | QD | CRS
1900-01-01 | #REF! | #REF! | Waiting for action | 0140/DFSL/10 | 2011-01-18 | 2011-02-01 | -2080 | O+A |  |  |  | Extention | Level 2 | O+A | N/A | N/A | QD | QD | Maintenance Records
1900-01-02 | #REF! | #REF! | Waiting for action | 0140/DFSL/10 | 2011-01-18 | 2011-02-01 | -2080 | O+A |  |  |  | Rejected | Level 3 | O+E | B-MAK | A319-132 | ED | ED | Maintenance Data
1900-01-03 | #REF! | #REF! | Waiting for action | 0140/DFSL/10 | 2011-01-18 | 2011-02-01 | -2080 | O+A |  |  |  | Evidence | Level 3 | O+R | B-MAL | A319-132 | PPC | PPC | Training Records
1900-01-04 | #REF! | #REF! | Answered | QD/AAC/11-022 | 2011-01-27 | N/A | N/A | O+A | To revise MEPM L 2.4.1 paragraph 14 to read that" ...... across the MAR 145.50 and; write the JMM number and the origin LAA approval Certificate number. " to meet the JMM requirement. | To revise MEPM L 2.4.1 paragraph 14 to read that" ...... across the MAR 145.50 and. write the JMM number and the origin LAA approval Certificate number. " to meet the JMM requirement. Notify relevant LM service Providers to follow the new procedures. |  | Closed |  | Closed | B-MAM | A319-132 | AMD | AMD | Marking
1900-01-05 | #REF! | #REF! | Answered | QD/AAC/11-022 | 2011-01-27 | N/A | N/A | O+A | The MEL TR No.-2S/0 lA issue 01 has been issued and under approval. it will be inserted into MEL for reference. also, Alert to add UPK was accomplished. therefore. TN A320-00303 Rev. 01 is unnecessary to be sent out to Out Stations. | The TN master control list will be provided to Out Stations for their information whenever there is a TN relate to Out Stations. |  | Waiting for action |  | Evidence | B-MAN | A319-132 | MCC | MCC | Repair approval
1900-01-06 | #REF! | #REF! | Answered | QD/AAC/11-022 | 2011-01-27 | N/A | N/A | O+A | To check the AMASIS database and if found the material is still within shelf life limit. To reissue Material Sticker for the mentioned AeroShell Grease 7 and Skydrol LD4 individual container. | 1. Request QCls to strictly follow the MEPM procedure 2.2.1 & 2.2.2 to ensure Material Sticker are issued and attached to relevant materials at individual container basis. 2. To revise MEPM procedure 2.3.2 to request LM Technicians to report any loss of sticker promptly to Material Recourses who will check the AMASIS database and if found the matetial is still within shelf life limit, to inform QCI to reissue the sticker. |  | Waiting for AACM answer |  |  | B-MAO | A319-132 | A320 | A320 | Remedial action
1900-01-07 | #REF! | #REF! | Answered | QD/AAC/11-022 | 2011-01-27 | N/A | N/A | O+A | Material Resource on-site representative was requested to search for proper container in local for keeping the type of DG material. | The relevant staff was notified about this issue and called back from PEK to MFM for renew training on 20-Jan-20 11. |  | N/A |  |  | B-MAH | A320-232 | A300 | A300 | Feedback System
1900-01-08 | #REF! | #REF! | Evidence | email from stephen | 2011-01-31 | N/A | N/A | Evidence |  |  |  | acceptable
1900-01-09 | #REF! | #REF! | acceptable | email from stephen | 2011-01-31 | N/A | N/A | Closed
1900-01-10 | #REF! | #REF! | Waiting for action | email from stephen | 2011-01-31 | 2011-02-14 | -2067 | O+A
1900-01-11 | #REF! | #REF! | Evidence | email from stephen | 2011-01-31 | N/A | N/A | Evidence
1900-01-14 | #REF! | #REF! | Answered | Answer to AACM | 2011-03-09 | N/A | N/A | O+A
1900-01-15 | #REF! | #REF! | Answered | 0691/DFSL/11 | 2011-03-22 | N/A | N/A | Closed
1900-01-08 | #REF! | #REF! | N/A | 0691/DFSL/11 | 2011-03-22 | N/A | N/A | Closed |  |  |  | acceptable
1900-01-09 | #REF! | #REF! | N/A | 0691/DFSL/11 | 2011-03-22 | N/A | N/A | Closed
1900-01-10 | #REF! | #REF! | N/A | 0691/DFSL/11 | 2011-03-22 | N/A | N/A | Closed
1900-01-11 | #REF! | #REF! | N/A | email from stephen | 2011-01-31 | N/A | N/A | O+A
| #REF! | #REF! |  |  |  |  | -42655
-42655
-42655
-42655
-42655
-42655
Formulas:
Days Left = [Due date]-TODAY()
Note on C1: Department / Division affected.
Note on I1: Close Open O+A=Open+Accepted O+E=Open+Extension A+W=answered and waiting A+R=answered and rejected
Note on P3: OPEN+ANSWER
Note on P4: O+E=Open+Extension
Note on P5: Answered+Rejected